## Next.js + Redux Plan
# | Task Name | Time Estimate (hrs) | Remarks
1 | Scaffold Next.js app (TypeScript, App Router) | 0.5 | Create frontend app alongside existing time-tracker-backend; configure ESLint/Prettier and folder structure (app/, components/, features/).
2 | Install & configure Redux Toolkit + React-Redux | 0.5 | Set up store.ts, root reducer, typed hooks (useAppDispatch/useAppSelector), and wrap app in <Provider> via a client-side layout wrapper.
3 | Build API client layer (Axios) for backend | 0.5 | Base URL config via env vars (NEXT_PUBLIC_API_URL), Axios instance, and typed request helpers matching API.md endpoints for Project/Task/State.
4 | Create projectsSlice (RTK) with async thunks | 0.5 | CRUD thunks for GET/POST/PUT/DELETE /Project; loading/error state handling.
5 | Create tasksSlice (RTK) with async thunks | 0.5 | CRUD + PATCH thunks for /Task, plus parent/nested task fetch endpoints (/Task/parent/{projectId}, /Task/nested/{parentTaskId}).
6 | Create statesSlice (RTK) with async thunks | 0.3 | CRUD thunks for /State; used to drive task status columns.
7 | Build Projects list page + navigation | 0.5 | Route: /projects - list, create, edit, delete projects; links into project detail/task board.
8 | Build Project create/edit form with rich text editor | 0.75 | Integrate TipTap for description field (HTML) per API.md rich-text contract; connect to projectsSlice.
9 | Build Task board page (parent + nested tasks) | 0.75 | Route: /projects/[id] - render parent tasks and expandable nested subtasks using tasksSlice selectors.
10 | Build Task create/edit form with rich text editor | 0.5 | TipTap-based description editor for tasks; supports parentID selection and projectID association.
11 | Implement State-based Kanban columns (new feature) | 0.5 | Group tasks by stateID into columns (Pending/In Progress/etc.) sourced from statesSlice; improves on current flat list.
12 | Add drag-and-drop status update (new feature) | 0.5 | Use dnd-kit to move tasks between state columns, dispatching PATCH /Task/{id} on drop.
13 | Add live time-tracking timer (new feature) | 0.5 | Start/stop timer UI per task that accumulates into timeTaken and PATCHes the backend on stop.
14 | Set up Tailwind CSS design system | 0.3 | Base styling, theme tokens, and shared layout components for consistent UI.
15 | Add global error/loading UI states | 0.3 | Toast notifications, skeleton loaders, and error boundaries wired to Redux async states.
16 | Environment & deployment configuration | 0.3 | next.config.js, .env.example, CORS check against ASP.NET backend, and README update for running both apps together.
17 | Smoke test & manual QA pass | 0.3 | Run app against local backend; verify project/task CRUD, drag-and-drop, and timer flows end-to-end.
Total